## Sheet1
Development Plan
Members |  | 2019-08-27 | 2019-08-28 | 2019-08-30 | 2019-08-31 | 2019-09-03 | 2019-09-06 | 2019-09-10 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20
Raymond |  | Revised Need Finding |  |  | Recording and Interview of Prototype | Review User Feedback |  | Started Creating Digital Prototype | Finished Prototype | Review User Feedback | Revised NeedFinding | Presentation
John Paul |  | 2019-08-28: Rework on Paper Prototype Design; 2019-09-03: Editing of Video; 2019-09-06: Design Wireframe; 2019-09-17: Started Demo and Interview; 2019-09-18: Video Editing